PROJECT PROPOSAL

Strengthening Women's Livelihoods and Household Nutrition in Arki Block

An integrated economic empowerment and maternal-child nutrition initiative

Location: Arki Block, Khunti District, Jharkhand

Duration: 24 months

Budget: INR 60,00,000

Submitted to: Grameen Vikas Foundation

Submitted by: Prakash Kumar

Contents

# Problem Statement

Scheduled Tribe women of reproductive age in the landless households of Arki block face two intertwined challenges: economic vulnerability and a heavy burden of maternal and child undernutrition. Together these hold households within a cycle of poverty and poor health.

These women depend on rain-fed agriculture and forest produce, own little land, and have no stable off-farm income. A majority of pregnant women are anaemic, and child stunting ranks among the highest in the country.

# Project Objective

To strengthen the economic independence of 800 Scheduled Tribe women in Arki block while improving maternal and child nutrition over 24 months.

# Operational Strategy

The project adopts an integrated, community-platform approach anchored in women's Self-Help Groups, sequenced across three phases and converging with government systems including NRLM, MGNREGA, ICDS and NHM.

# Activities

Activities are grouped by output and every activity traces to a defined result: mobilisation across 16 Gram Panchayats, SHG formation, skills training, asset support, kitchen gardens, and convergence with frontline health and nutrition services.

# Results Framework

| Level | Result statement | Indicator | Baseline | Target | Means of verification |
| --- | --- | --- | --- | --- | --- |
| Impact | Reduced poverty and malnutrition among ST households | Under-5 stunting prevalence | 39.6% (NFHS-5) | Below block baseline | Endline survey |
| Outcome 1 | 800 women have increased incomes | Average annual income | To be established | ≥50% increase | Income survey |
| Output 1.1 | Women trained in livelihood skills | Women completing training | 0 | 800 women | Attendance registers |

# Sustainability

Sustainability rests on federated SHGs, retained access to capital, changed practices within the community, and handover to established public programmes.

# Budget

| Item | Unit | Unit cost | Qty | Total | Source |
| --- | --- | --- | --- | --- | --- |
| Project Coordinator | month | 35,000 | 24 | 8,40,000 | NRLM norms |
| Community Mobilisers (5) | month | 15,000 | 24 | 18,00,000 | Field-staff rates |
| Livelihood skills training | batch of 40 | 30,000 | 20 | 6,00,000 | NRLM norms |